## Sheet1
Activity | Indicative weather threshold
Reduced crane operation at construction sites | Multiple thresholds depending on crane size and specification. Indicative wind speed thresholds for stopping operations include:
tower cranes 20m/s
crawler cranes 16m/s
lifting of persons 7m/s
Viaduct Launching Girder 7m/s (movement) and 11m/s (lifting)
(Note wind direction will also be important but is site specific).
Concrete pouring activities | Limited to temperatures between 0°C and 40°C
Masonry works | Cannot occur in temperatures below 4°C
Earthworks and excavation activities | Challenging when mean temperature ≤0°C or precipitation ≥10mm/day
Increased need for management of vegetation | During heatwave or dry spell periods
Need for additional breaks for outside workers during heatwave conditions | When daily maximum temperatures exceed heatwave conditions for the given location.
Drone flying activities | Become challenging above wind speeds of ~8m/s
• Heatwave | a period of at least three consecutive days with daily maximum temperatures meeting or exceeding 25-28°C (depending on location within the country, details can be found here: https://www.metoffice.gov.uk/weather/learn-about/weather/types-of-weather/temperature/heatwave#:~:text=A%20UK%20heatwave%20threshold%20is,updated%20ahead%20of%20summer%202022.)
• Dry spell | at least 10 consecutive days where rainfall is <1mm