## Hack Risk Register
Project Hack Risk Register Dataset for 17.13
Risk Details | [9 empty] | Current Assessment | [8 empty] | Mitigations and Target Assessments | [6 empty] | Updates
Ref | Threat or Opportunity | Project | WBS | Risk Title | Risk Description "There is a risk…" | Risk Cause "…caused by…" | Risk Consequence "…resulting in…" | Risk Owner | Risk Proximity | Probability (1-5) | Severity (1-5) | Risk Rating (1-25) | Prob (%) | Min Impact (Cost) | Most Likely Impact (Cost) | Max Impact (Cost) | Current Risk Value* | Justification | Manageability | Required Mitigating Actions | Probability (1-5) | Severity (1-5) | Risk Rating (1-25) | Action Owner (Named Person) | Action Due Date | Comments/Updates | Status Open / Closed | Date Closed | Date Reviewed
GLDS_001 | Opportunity | Project Sunset | 04- Design | Project Acceleration Opportunity | There is an opportunity that the programme can be accelerated on Project Sunset | Caused by improved performance of design team | Resulting in potential programme acceleration and ability to start construction earlier | A.Turing | 0-3 months | 3 | -5 | -15 | 50% | 0 | 0 | -25000000 | -4166666.6667 | Min - ML - Max- Cost per week of 8 weeks saving | Reasonable Ability to Influence & Manage | Scope lockdown and certainty required. Design team to identify opportunities for time saving and seek approval at earliest moment | 4 | -5 | -20 | A.Turing | 31st Dec 22 |  | Open |  | 26.08.22
GLDS_002 | Threat | Project Dejavu | 06- Construction | Supply Chain Buy-In | There is a risk that the supply chain are do not buy into construction programme | Caused by the supply chain having limited input to the latest schedule | Resulting in potential changes to the construction programme and subsequent knock-on effects | M.Faraday | Now | 3 | 5 | 15 | 50% | 0 | 5000000 | 15000000 | 3333333.3333 | Min- No impact and deliver ML- 4 week impact (renegotiating/resource allocation delays) Max- 12 week impact associated with having to retender packages where contractors cannot meet the programme. Knock-on to other trades | Strong Ability to Influence & Manage | As early as possible engagement with supply chain required to buy-in to new programme as well as secure available resources | 3 | 3 | 9 | L.Da Vinci | 1st Jan 23 |  | Open |  | 10.10.22
GLDS_003 | Threat | Project Dejavu | 08- Operations / Maintenance | Commissioning Programme Lacks Robustness | There is a risk that the commissioning programme is not robust enough i.e. no terminal float | Caused by limited programme float and a process still to be agreed | Resulting in commissioning programme delay or overrun subsequently delaying Project Dejavu opening | M.Faraday | 6-12 months | 2 | 5 | 10 | 25% | 0 | 1000000 | 5000000 | 500000 | Min- No impact and deliver ML- 2 week impact Max- 8 week impact associated Operations delay in handover approval | Low Ability to Influence & Manage | Sequencing of sectional completion and planned commissioning resource to be test in commission ability reviews Overarching Commissioning Strategy to be completed and approved that outlines responsibilities, deliverables, planned activities etc and is signed up to by all parties | 1 | 4 | 4 | L.Pasteur | 1st Dec 22 |  | Open |  | 07.09.22
GLDS_004 | Threat | Corporate | 09- Corporate | Unable to resource specialists | There is a risk that the projects are unable to secure specialist resources to enable delivery of their programme | Caused by limited specialist resource in the marketplace and HR delays | Resulting in delays to programme caused by under resourcing | M.Curie | 0-3 months | 5 | 2 | 10 | 75% | 0 | 50000 | 75000 | 31250 | Min- No impact ML- Min delay, but premium paid in some instances Max- Associated delay with being unable to secure specialist resource up to 6 weeks (linked to any overall programme) | Strong Ability to Influence & Manage | Monitoring of the quantity and type of resource on site compared to the planned level of resources will provide early indications of issues so that action can be taken. | 3 | 3 | 9 | M.Curie | 3rd March 23 |  | Open |  | 26.08.22
GLDS_005 | Threat | Project Sunset | 06- Construction | Knowledge gaps | There is a risk that the existing project team disappear as the project heads to conclusion leaving critical knowledge gaps | Caused by a buoyant construction market and inability to secure key resource to project end | Resulting in loss of critical project knowledge, potentially delaying contentious sign-off areas | A.Turing | 6-12 months | 3 | 2 | 6 | 40% | 100000 | 250000 | 500000 | 113333.3333 | Min- 3 Key People ML - 7 Key People Max- Assumed 10 Key People @ £50k | Reasonable Ability to Influence & Manage | Ongoing programme to drive Life discussions and capture/disseminate key lessons Consider joint KPIs/ incentives re. retention | 3 | 2 | 6 | M.Curie | 31st Dec 22 |  | Open |  | 07.09.22
GLDS_006 | Threat | Project Dejavu | 04- Design | Late Design Issues | There is a risk that there are more design issues at large that have yet to be uncovered | Caused by not all design being frozen and procurement activities outstanding | Resulting in delay to procurement and construction programme | J.Maxwell | 0-3 months | 3 | 4 | 12 | 50% | 1000000 | 5000000 | 15000000 | 3500000 | Min- Minimal impact ML- Additional resource costing and a level of delay (disruption and additional work) Max- Additional delays and design resource costings with knock-on impacts on rework | Low Ability to Influence & Manage | Proactive resolution process in place and needs to be continued i.e. design issues likely to crop up as and when, how the project actively responds is key. | 2 | 4 | 8 | J.Maxwell | 1st Mar 23 |  | Open |  | 07.09.22
GLDS_007 | Threat | Project Whistler | 07- Technical | Quantum of Rework | There is a risk that the quantum of rework does not reduce | Caused by significant volume of existing rework and potential future rework | Resulting in inability to perform to programme and increased aftercare/defect costs | N.Tesla | Now | 3 | 5 | 15 | 50% | 1000000 | 5000000 | 7500000 | 2250000 | Min- Minimal impact ML- Additional resource costing and a level of delay (disruption and additional work) Max- Additional delays and design resource costings with knock-on impacts on rework | Low Ability to Influence & Manage | Develop better metrics with BIM 360 and close outs with detailed programmes incorporating the close out sequences and durations. Improve and achieve a consistent level of quality control and avoid repeat issues occurring. | 2 | 5 | 10 | N.Tesla | 31st Oct 22 |  | Open |  | 15.10.22
GLDS_008 | Threat | Project Whistler | 07- Technical | Commissioning Failure | There is a risk of system integration failure/faults etc that arise in Commissioning causing significant rework | Caused by complexity associated with commissioning and compliance | Resulting in significant rework | N.Tesla | Now | 3 | 2 | 6 | 40% | 50000 | 200000 | 750000 | 133333.3333 | Min- ML- Increased costs associated with rework but min prog delay Max- Critical delay with additional equipment required and rework | Reasonable Ability to Influence & Manage | Drive programme of improved monitoring and quality controls throughout MEP system integration process. | 2 | 2 | 4 | N.Tesla | 31st Oct 22 |  | Open |  | 15.10.22
GLDS_009 | Threat | Project Dejavu | 05- Commercial/ Procurement | Handover Documentation | There is a risk that the level of handover documentation is underestimated causing programme delay | Caused by underestimation of handover documentation required and approval process | Resulting in handover programme delay | J.Maxwell | 6-9 months | 3 | 2 | 6 | 40% |  | 300000 | 6000000 | 1260000 | Best case is no impact - zero Worst case would be a 4 week delay - currently project monthly spend as £ 1.5m | Strong Ability to Influence & Manage | Agree hierarchy and map out responsibilities for documentation handover (i.e. Building and Fire Control) | 2 | 2 | 4 | J.Maxwell | 30 June '23 |  | Open |  | 26.08.22
GLDS_010 | Threat | Corporate | 09- Corporate | Fire & Safety Bill underestimation | There is a risk that the imminent updates to the Fire & Safety Bill are underestimated/implemented too late | Caused by lack of understanding of the latest Fire & Safety Bill changes | Resulting in increased requirements for records and records keeping that put additional strain on project programme and resources | R.Franklin | Now | 3 | 4 | 12 | 40% | 0 | 3000000 | 4000000 | 933333.3333 | Best case is no impact - zero Worst case open up facades and reinstall all fire safety. 4 weeks impact @ £1m per week | Low Ability to Influence & Manage | R.Franklin to ask FS experts to come to all sites and present FS latest | 1 | 5 | 5 | R.Franklin | 25th Dec '23 |  | Open |  | 07.09.22
GLDS_011 | Threat | Corporate | 09- Corporate | New Legislation | There is a risk that new legislation/ways working require to be applied retrospectively | Caused by changes in legislation and ways of working since the project began | Resulting in late changes to design, construction and commissioning | R.Franklin | 12-15 months | 1 | 5 | 5 | 5% | 0 | 0 | 10000000 | 166666.6667 | Max- Impact presumed to apply to all projects | Low Ability to Influence & Manage | Investigate and publish all legislative changes since projects started. Further review to look ahead at current planned legislative changes up to 2024 to enable the direction as required | 1 | 3 | 3 | R.Franklin | 26th Dec '23 |  | Open |  | 26.08.22
GLDS_012 | Threat | Project Sunset | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | A.Turing | Now | 4 | 4 | 8 | 60% | 50000 | 100000 | 800000 | 190000 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust require re-procured | Reasonable Ability to Influence & Manage | Consider early/advance payment to mitigate insolvency challenges Retain best performing s/c - SME ensure contingency in delivery team | 4 | 2 | 8 | I.Newton | 31st Oct 22 |  | Open |  | 26.08.22
GLDS_013 | Threat | Project Dejavu | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | I.Newton | 6-9 months | 2 | 2 | 8 | 20% | 0 | 100000 | 400000 | 33333.3333 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust requiring replacing and associated delays (Reprocure and Premium costs) | Reasonable Ability to Influence & Manage | Consider early/advance payment to mitigate insolvency challenges Retain best performing s/c - SME ensure contingency in delivery team | 1 | 2 | 2 | I.Newton | 2nd Feb'23 |  | Open |  | 26.08.22
GLDS_014 | Threat | Project Whistler | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | I.Newton | 6-9 months | 4 | 2 | 8 | 55% | 0 | 100000 | 400000 | 91666.6667 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust requiring replacing and associated delays (Reprocure and Premium costs) | Reasonable Ability to Influence & Manage | Consider early/advance payment to mitigate insolvency challenges Retain best performing s/c - SME ensure contingency in delivery team | 2 | 2 | 4 | I.Newton | 1st Mar 23 |  | Open |  | 26.08.22
GLDS_015 | Threat | Corporate | 05- Commercial/ Procurement | Increased Inflation | There is a risk of increased inflation to materials and labour that impacts all projects | Caused by project allowances not being sufficient to meet future inflation changes | Resulting in increased Corporate Funding costs for all projects | I.Newton | Now | 3 | 5 | 15 | 66% | 0 | 5000000 | 25000000 | 6600000 | ML- £1m per project Max- £5m per project | Low Ability to Influence & Manage | Further review and challenge inflation assumptions/assessments that have been made in the baseline costs. Consider who holds this risk and whether an additional risk allowance is required for 'over and above's'. Could present an opportunity if inflation reduces | 2 | 2 | 4 | I.Newton | 31st Oct 22 |  | Open |  | 22.09.22
GLDS_016 | Threat | Project Whistler | 07- Technical | Equipment availability | There is a risk that due to the previous prog delay that some equipment is no longer available | Caused by required equipment now being obsolete | Resulting in further delay associated with re-procurement and design changes in relation to spacing/room conditions | N.Tesla | 6-9 months | 1 | 4 | 4 | 35% | 600000 | 1500000 | 4000000 | 711666.6667 | Max- impact on all systems - 4 months total impact and systems reconfigured | Strong Ability to Influence & Manage | Engagement with all equipment suppliers is required when revised dates are know to establish any equipping changes. | 1 | 4 | 4 | N.Tesla | 2022-12-30 |  | Open |  | 22.09.22
GLDS_017 | Threat | Project Whistler | 08- Operations / Maintenance | Lack of extended warranties | There is a risk that due to the prog delay that equipment already purchased will require extended warranties or extended warranties will not be possible | Caused by overall programme delay and some equipment already being in receipt | Resulting in additional project costs to extend warranties | N.Tesla | 6-9 months | 3 | 1 | 3 | 30% | 10000 | 20000 | 50000 | 8000 | Max- Extended Warranties of 5 systems required | Strong Ability to Influence & Manage | Clarity required as to which equipment require extended warranties and begin to engage with suppliers This needs to be itemised and quantified to understand the scale of the potential issue. | 1 | 2 | 2 | N.Tesla | 2022-12-31 |  | Open |  | 07.09.22
GLDS_018 | Threat | Project Dejavu | 03- Existing Assets | Utilities Failure | There is a risk that any Utilities (Water, Power, Gas, Telecom) fail or is insufficient | Caused by performance issues associated with given utility | Resulting in additional rework and programme delay | M.Faraday | Now | 2 | 4 | 8 | 20% | 0 | 750000 | 2500000 | 216666.6667 | Max- All Utilities fail | Strong Ability to Influence & Manage | Mitigations completed | 1 | 1 | 1 | M.Faraday | 9th Sept 22 |  | Closed | 07.09.22 | 07.09.22
GLDS_019 | Threat | Project Whistler | 01- Strategic/ Programme | Culture & Behaviours | There is a risk that given the projects past performance can the project team change behaviours sufficiently to allow collaboration across the project to drive performance. | Caused by historical project behaviours and lack of collaborative ways of working | Resulting in challenging project delivery and potential further delays | M.Curie | 0-3 months | 5 | 5 | 25 | 50% | 0 | 100000 | 3000000 | 516666.6667 |  | Low Ability to Influence & Manage | Collaboration workshops to be set up amongst SLT and project teams Consider project team change as part of sell-off strategy | 3 | 3 | 9 | M.Curie | 1st Dec'22 |  | Open |  | 22.09.22
GLDS_020 | Threat | Project Sunset | 01- Strategic/ Programme | Culture & Behaviours | There is a risk that given the projects past performance can the project team change behaviours sufficiently to allow collaboration across the project to drive performance. | Caused by historical project behaviours and lack of collaborative ways of working | Resulting in challenging project delivery and potential further delays | M.Curie | 0-3 months | 3 | 5 | 15 | 50% | 0 | 100000 | 500000 | 100000 |  | Low Ability to Influence & Manage | Collaboration workshops to be set up amongst SLT and project teams | 3 | 3 | 9 | M.Curie | 31st Dec'22 |  | Open |  | 22.09.22
GLDS_021 | Threat | Project Sunset | 03- Existing Assets | Utilities Failure | There is a risk that any Utilities (Water, Power, Gas, Telecom) fail or is insufficient | Caused by performance issues associated with given utility | Resulting in additional rework and programme delay | A.Turing | Now | 5 | 4 | 20 | 80% | 0 | 7500000 | 10000000 | 4666666.6667 | Max- All Utilities fail re. full redesign and remediation | Low Ability to Influence & Manage | 1. Water - Utilities Inc to sign make final connection agreement 2. Gas - GB Gas to confirm incoming supply is sufficient | 3 | 5 | 15 | A.Turing | 31st Jan '23 |  | Open |  | 07.09.22
GLDS_022 | Opportunity | Project Sunset | 05- Commercial/ Procurement | Opportunity to In-House Procure | There is an opportunity for the in-house delivery team to conduct the works rather than externals | Caused by recent recruitment of technical specialists | Resulting in 'costs' to deliver being diverted internally | A.Turing | Now | 4 | -2 | -8 | 95% | -25000 | -200000 | -1000000 | -387916.6667 | Max- All delivery contracts diverted internally | Strong Ability to Influence & Manage | Internal team to provide capability statement and proposal for carrying out the works | 5 | -2 | -10 | A.Turing | 31st Dec'22 |  | Open |  | 07.09.22
GLDS_023 | Threat | Corporate | 09- Corporate | Lack of funding for Christmas Parties | There is a risk that due to poor corporate performance there is no budget for Christmas parties | Caused by poor investment decisions and delay in procuring Project Whistler | Resulting in poor staff morale and reputational damage | R.Franklin | Now | 5 | 2 | 10 | 90% | 0 | 100000 | 275000 | 112500 | Max- Staff replacement/recruitment costs | Reasonable Ability to Influence & Manage | Consider deferred Christmas parts to Q1 2023 to allow for potential investments to land | 4 | 1 | 4 | R.Franklin | 31st Dec'22 |  | Open |  | 07.09.22
GLDS_024 | Threat | Corporate | 01- Strategic/ Programme | Project Whistler Mothball | There is a risk that the SLT decide to mothball Project Whistler | Caused by poor project and team performance and potential lack of RoI | Resulting in significant revenue stream loss and reputational damage | R.Franklin | 3-6 months | 4 | 5 | 20 | 75% | 5000000 | 12500000 | 20000000 | 9375000 | ML- Revenue loss Max- Investor repayment and revenue loss | Low Ability to Influence & Manage | Seek project buy-out investment from Corp X | 3 | 4 | 12 | N.Tesla | 31st Jan '23 |  | Open |  | 10.10.22

## Dropdowns
| Project List | WBS | Risk Proximity | Risk Status | Manageability | Risk Owner
Threat | Corporate | 01- Strategic/ Programme | Now |  | Strong Ability to Influence & Manage | A.Turing
Opportunity | Project Dejavu | 02- Planning | 0-3 months | OPEN | Reasonable Ability to Influence & Manage | I.Newton
| Project Sunset | 03- Existing Assets | 3-6 months |  | Low Ability to Influence & Manage | J.Maxwell
| Project Whistler | 04- Design | 6-9 months | CLOSED |  | L.Da Vinci
|  | 05- Commercial/ Procurement | 9-12 months |  |  | L.Pasteur
|  | 06- Construction | 12+ months | CLOSED - EWN |  | M.Curie
|  | 07- Technical |  |  |  | M.Faraday
|  | 08- Operations / Maintenance |  | CLOSED - CE |  | N.Tesla
|  | 09- Corporate |  |  |  | R.Franklin

## Risk Scoring Matrix
Probability |  | Score | Impact
Qualitative | Percentage |  | Capex Cost | Schedule | Qualitative | Key | Status
Very Unlikely | <10% | 1 | <£50k impact | Up to a month delay to non-critical path activities | Very Low | Open | Open
Unlikely | 10-30% | 2 | £50k-£500k | >1 months delay to non-critical path activities | Low | Closed | Closed
Probable | 30-50% | 3 | £500k - £1m | Up to a month delay to critical path activities | Medium | Closed - EWN | Closed - EWN
Likely | 50-80% | 4 | £1m- 3m | 1-3 months delay to critical path activities | High | Closed CE | Closed CE
Highly Likely | >80% | 5 | >£3m | >3 months delay to critical path activities | Very High
Risk Proximity
Now
0-3 months
0-6 months
0-9 months
0-12 months
0-15months
0-18months
0-24 months
3-6 months
6-9 months
6-12 months
9-12 months
9-15 months
12-15 months