## query (13)
Risk ID | ProjectRef | AddedBy | DateAdded | ReviewStatus | ThreatorOpp | Project | WBS | RiskTitle | RiskDescription | RiskCause | RiskConsequence | RiskOwner | RiskProximity | Probability | Severity | Prob | MinImpact | MostLikelyImpact | MaxImpact | CurrentRiskValue | Justification | Manageability | PM Probability | PMSeverity | Risk Rating | Comments/Updates | OverallStatus | Date Closed | Date Reviewed | Item Type | Created | Approval | PMRiskRating | ID | Item Type2 | Path
GLDS_001 | Project001 | John Smith | 2023-01-11 | Draft | Opportunity | Project Sunset | 04- Design | Project Acceleration Opportunity | There is an opportunity that the programme can be accelerated on Project Sunset | Caused by improved performance of design team | Resulting in potential programme acceleration and ability to start construction earlier | A.Turing | 0-3 months | 3 | -5 | 0.5 | 0 | 0 | -25000000 | -4166666.6667 | Min - ML - Max- Cost per week of 8 weeks saving | Reasonable Ability to Influence & Manage | 4 | -5 | -20 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 1 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_002 | Project001 | John Smith | 2022-01-02 | Accepted | Threat | Project Dejavu | 06- Construction | Supply Chain Buy-In | There is a risk that the supply chain are do not buy into construction programme | Caused by the supply chain having limited input to the latest schedule | Resulting in potential changes to the construction programme and subsequent knock-on effects | M.Faraday | Now | 3 | 5 | 0.5 | 0 | 5000000 | 15000000 | 3333333.3333 | Min- No impact and deliver ML- 4 week impact (renegotiating/resource allocation delays) Max- 12 week impact associated with having to retender packages where contractors cannot meet the programme. Knock-on to other trades | Strong Ability to Influence & Manage | 3 | 3 | 9 |  | Open |  | 2022-10-10 | Item | 2022-11-28 14:51 |  |  | 2 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_003 | Project001 | Martin Paver | 2022-11-07 | Rejected | Threat | Project Dejavu | 08- Operations / Maintenance | Commissioning Programme Lacks Robustness | There is a risk that the commissioning programme is not robust enough i.e. no terminal float | Caused by limited programme float and a process still to be agreed | Resulting in commissioning programme delay or overrun subsequently delaying Project Dejavu opening | M.Faraday | 6-12 months | 2 | 5 | 0.25 | 0 | 1000000 | 5000000 | 500000 | Min- No impact and deliver ML- 2 week impact Max- 8 week impact associated Operations delay in handover approval | Low Ability to Influence & Manage | 1 | 4 | 4 |  | Open |  | 2022-07-09 | Item | 2022-11-28 14:51 |  |  | 3 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_004 | Project001 | Martin Paver | 2022-11-16 | Draft | Threat | Corporate | 09- Corporate | Unable to resource specialists | There is a risk that the projects are unable to secure specialist resources to enable delivery of their programme | Caused by limited specialist resource in the marketplace and HR delays | Resulting in delays to programme caused by under resourcing | M.Curie | 0-3 months | 5 | 2 | 0.75 | 0 | 50000 | 75000 | 31250 | Min- No impact ML- Min delay, but premium paid in some instances Max- Associated delay with being unable to secure specialist resource up to 6 weeks (linked to any overall programme) | Strong Ability to Influence & Manage | 3 | 3 | 9 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 4 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_005 | Project001 | Alex Elderton | 2022-11-16 | Draft | Threat | Project Sunset | 06- Construction | Knowledge gaps | There is a risk that the existing project team disappear as the project heads to conclusion leaving critical knowledge gaps | Caused by a buoyant construction market and inability to secure key resource to project end | Resulting in loss of critical project knowledge, potentially delaying contentious sign-off areas | A.Turing | 6-12 months | 3 | 2 | 0.4 | 100000 | 250000 | 500000 | 113333.3333 | Min- 3 Key People ML - 7 Key People Max- Assumed 10 Key People @ £50k | Reasonable Ability to Influence & Manage | 3 | 2 | 6 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 5 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_006 | Project001 | Martin Paver | 2022-11-24 | Draft | Threat | Project Dejavu | 04- Design | Late Design Issues | There is a risk that there are more design issues at large that have yet to be uncovered | Caused by not all design being frozen and procurement activities outstanding | Resulting in delay to procurement and construction programme | J.Maxwell | 0-3 months | 3 | 4 | 0.5 | 1000000 | 5000000 | 15000000 | 3500000 | Min- Minimal impact ML- Additional resource costing and a level of delay (disruption and additional work) Max- Additional delays and design resource costings with knock-on impacts on rework | Low Ability to Influence & Manage | 2 | 4 | 8 |  | Open |  | 2022-07-09 | Item | 2022-11-28 14:51 |  |  | 6 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_007 | Project001 | John Smith | 2022-11-06 | Accepted | Threat | Project Whistler | 07- Technical | Quantum of Rework | There is a risk that the quantum of rework does not reduce | Caused by significant volume of existing rework and potential future rework | Resulting in inability to perform to programme and increased aftercare/defect costs | N.Tesla | Now | 3 | 5 | 0.5 | 1000000 | 5000000 | 7500000 | 2250000 | Min- Minimal impact ML- Additional resource costing and a level of delay (disruption and additional work) Max- Additional delays and design resource costings with knock-on impacts on rework | Low Ability to Influence & Manage | 2 | 5 | 10 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 7 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_008 | Project001 | John Smith | 2022-10-18 | Accepted | Threat | Project Whistler | 07- Technical | Commissioning Failure | There is a risk of system integration failure/faults etc that arise in Commissioning causing significant rework | Caused by complexity associated with commissioning and compliance | Resulting in significant rework | N.Tesla | Now | 3 | 2 | 0.4 | 50000 | 200000 | 750000 | 133333.3333 | Min- ML- Increased costs associated with rework but min prog delay Max- Critical delay with additional equipment required and rework | Reasonable Ability to Influence & Manage | 2 | 2 | 4 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 8 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_009 | Project001 | Warwick Gross | 2022-09-06 | Accepted | Threat | Project Dejavu | 05- Commercial/ Procurement | Handover Documentation | There is a risk that the level of handover documentation is underestimated causing programme delay | Caused by underestimation of handover documentation required and approval process | Resulting in handover programme delay | J.Maxwell | 6-9 months | 3 | 2 | 0.4 |  | 300000 | 6000000 | 1260000 | Best case is no impact - zero Worst case would be a 4 week delay - currently project monthly spend as £ 1.5m | Strong Ability to Influence & Manage | 2 | 2 | 4 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 9 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_010 | Project001 | Warwick Gross | 2022-11-15 | Accepted | Threat | Corporate | 09- Corporate | Fire & Safety Bill underestimation | There is a risk that the imminent updates to the Fire & Safety Bill are underestimated/implemented too late | Caused by lack of understanding of the latest Fire & Safety Bill changes | Resulting in increased requirements for records and records keeping that put additional strain on project programme and resources | R.Franklin | Now | 3 | 4 | 0.4 | 0 | 3000000 | 4000000 | 933333.3333 | Best case is no impact - zero Worst case open up facades and reinstall all fire safety. 4 weeks impact @ £1m per week | Low Ability to Influence & Manage | 1 | 5 | 5 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 10 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_011 | Project001 | Alex Elderton | 2022-11-07 | Accepted | Threat | Corporate | 09- Corporate | New Legislation | There is a risk that new legislation/ways working require to be applied retrospectively | Caused by changes in legislation and ways of working since the project began | Resulting in late changes to design, construction and commissioning | R.Franklin | 12-15 months | 1 | 5 | 0.05 | 0 | 0 | 10000000 | 166666.6667 | Max- Impact presumed to apply to all projects | Low Ability to Influence & Manage | 1 | 3 | 3 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 11 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_012 | Project001 | John Smith | 2022-11-14 | Accepted | Threat | Project Sunset | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | A.Turing | Now | 4 | 4 | 0.6 | 50000 | 100000 | 800000 | 190000 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust require re-procured | Reasonable Ability to Influence & Manage | 4 | 2 | 8 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 12 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_013 | Project001 | John Smith | 2022-12-02 | Accepted | Threat | Project Dejavu | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | I.Newton | 6-9 months | 2 | 2 | 0.2 | 0 | 100000 | 400000 | 33333.3333 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust requiring replacing and associated delays (Reprocure and Premium costs) | Reasonable Ability to Influence & Manage | 1 | 2 | 2 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 13 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_014 | Project001 | Martin Paver | 2022-09-05 | Accepted | Threat | Project Whistler | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | I.Newton | 6-9 months | 4 | 2 | 0.55 | 0 | 100000 | 400000 | 91666.6667 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust requiring replacing and associated delays (Reprocure and Premium costs) | Reasonable Ability to Influence & Manage | 2 | 2 | 4 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 14 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_015 | Project001 | Martin Paver | 2022-11-01 | Accepted | Threat | Corporate | 05- Commercial/ Procurement | Increased Inflation | There is a risk of increased inflation to materials and labour that impacts all projects | Caused by project allowances not being sufficient to meet future inflation changes | Resulting in increased Corporate Funding costs for all projects | I.Newton | Now | 3 | 5 | 0.66 | 0 | 5000000 | 25000000 | 6600000 | ML- £1m per project Max- £5m per project | Low Ability to Influence & Manage | 2 | 2 | 4 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 15 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_016 | Project001 | Alex Elderton | 2022-11-09 | Draft | Threat | Project Whistler | 07- Technical | Equipment availability | There is a risk that due to the previous prog delay that some equipment is no longer available | Caused by required equipment now being obsolete | Resulting in further delay associated with re-procurement and design changes in relation to spacing/room conditions | N.Tesla | 6-9 months | 1 | 4 | 0.35 | 600000 | 1500000 | 4000000 | 711666.6667 | Max- impact on all systems - 4 months total impact and systems reconfigured | Strong Ability to Influence & Manage | 1 | 4 | 4 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 16 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_017 | Project001 | Martin Paver | 2022-09-04 | Draft | Threat | Project Whistler | 08- Operations / Maintenance | Lack of extended warranties | There is a risk that due to the prog delay that equipment already purchased will require extended warranties or extended warranties will not be possible | Caused by overall programme delay and some equipment already being in receipt | Resulting in additional project costs to extend warranties | N.Tesla | 6-9 months | 3 | 1 | 0.3 | 10000 | 20000 | 50000 | 8000 | Max- Extended Warranties of 5 systems required | Strong Ability to Influence & Manage | 1 | 2 | 2 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 17 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_018 | Project001 | John Smith | 2022-09-05 | Rejected | Threat | Project Dejavu | 03- Existing Assets | Utilities Failure | There is a risk that any Utilities (Water, Power, Gas, Telecom) fail or is insufficient | Caused by performance issues associated with given utility | Resulting in additional rework and programme delay | M.Faraday | Now | 2 | 4 | 0.2 | 0 | 750000 | 2500000 | 216666.6667 | Max- All Utilities fail | Strong Ability to Influence & Manage | 1 | 1 | 1 |  | Closed | 2022-07-08 15:00 | 2022-07-09 | Item | 2022-11-28 14:51 |  |  | 18 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_019 | Project001 | John Smith | 2022-11-01 | Accepted | Threat | Project Whistler | 01- Strategic/ Programme | Culture & Behaviours | There is a risk that given the projects past performance can the project team change behaviours sufficiently to allow collaboration across the project to drive performance. | Caused by historical project behaviours and lack of collaborative ways of working | Resulting in challenging project delivery and potential further delays | M.Curie | 0-3 months | 5 | 5 | 0.5 | 0 | 100000 | 3000000 | 516666.6667 |  | Low Ability to Influence & Manage | 3 | 3 | 9 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 19 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_020 | Project001 | Warwick Gross | 2022-11-13 | Accepted | Threat | Project Sunset | 01- Strategic/ Programme | Culture & Behaviours | There is a risk that given the projects past performance can the project team change behaviours sufficiently to allow collaboration across the project to drive performance. | Caused by historical project behaviours and lack of collaborative ways of working | Resulting in challenging project delivery and potential further delays | M.Curie | 0-3 months | 3 | 5 | 0.5 | 0 | 100000 | 500000 | 100000 |  | Low Ability to Influence & Manage | 3 | 3 | 9 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 20 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_021 | Project001 | John Smith | 2022-09-06 | Draft | Threat | Project Sunset | 03- Existing Assets | Utilities Failure | There is a risk that any Utilities (Water, Power, Gas, Telecom) fail or is insufficient | Caused by performance issues associated with given utility | Resulting in additional rework and programme delay | A.Turing | Now | 5 | 4 | 0.8 | 0 | 7500000 | 10000000 | 4666666.6667 | Max- All Utilities fail re. full redesign and remediation | Low Ability to Influence & Manage | 3 | 5 | 15 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 21 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_022 | Project001 | John Smith | 2022-11-14 | Draft | Opportunity | Project Sunset | 05- Commercial/ Procurement | Opportunity to In-House Procure | There is an opportunity for the in-house delivery team to conduct the works rather than externals | Caused by recent recruitment of technical specialists | Resulting in 'costs' to deliver being diverted internally | A.Turing | Now | 4 | -2 | 0.95 | -25000 | -200000 | -1000000 | -387916.6667 | Max- All delivery contracts diverted internally | Strong Ability to Influence & Manage | 5 | -2 | -10 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 22 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_023 | Project001 | Martin Paver | 2022-11-14 | Draft | Threat | Corporate | 09- Corporate | Lack of funding for Christmas Parties | There is a risk that due to poor corporate performance there is no budget for Christmas parties | Caused by poor investment decisions and delay in procuring Project Whistler | Resulting in poor staff morale and reputational damage | R.Franklin | Now | 5 | 2 | 0.9 | 0 | 100000 | 275000 | 112500 | Max- Staff replacement/recruitment costs | Reasonable Ability to Influence & Manage | 4 | 1 | 4 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 23 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_024 | Project001 | Martin Paver | 2022-11-15 | Draft | Threat | Corporate | 01- Strategic/ Programme | Project Whistler Mothball | There is a risk that the SLT decide to mothball Project Whistler | Caused by poor project and team performance and potential lack of RoI | Resulting in significant revenue stream loss and reputational damage | R.Franklin | 3-6 months | 4 | 5 | 0.75 | 5000000 | 12500000 | 20000000 | 9375000 | ML- Revenue loss Max- Investor repayment and revenue loss | Low Ability to Influence & Manage | 3 | 4 | 12 |  | Open |  |  | Item | 2022-11-28 14:51 |  |  | 24 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
[5 empty] | Threat | Corporate | 08- Operations / Maintenance | Commissioning Programme Lacks Robustness | There is a risk that the commissioning programme is not robust enough i.e. no terminal float | Caused by limited programme float and a process still to be agreed | Resulting in commissioning programme delay or overrun subsequently delaying Project Dejavu opening |  | 6-9 months |  |  | 0 |  |  |  | 0 |  | Low Ability to Influence & Manage |  |  | 0 |  | OPEN |  | 2022-11-30 09:37 |  | 2022-11-30 09:37 |  | 0 | 41 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister
GLDS_25 |  | R.Franklin | 2022-11-30 09:41 |  | Threat | Project Sunset | 08- Operations / Maintenance | Commissioning Programme Lacks Robustness | There is a risk that the commissioning programme is not robust enough i.e. no terminal float | Caused by limited programme float and a process still to be agreed | Resulting in commissioning programme delay or overrun subsequently delaying Project Dejavu opening |  | 6-9 months |  |  | 0 |  |  |  | 0 |  | Low Ability to Influence & Manage |  |  | 0 |  | OPEN |  | 2022-11-30 09:41 |  | 2022-11-30 09:41 | approved | 0 | 42 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/PH17_RiskRegister