## Hack Risk Register
Project Hack Risk Register Dataset for 17.13
AddedBy | ReviewStatus | Risk ID | ThreatorOpp | Project | WBS | RiskTitle | RiskDescription | RiskCause | RiskConsequence | RiskOwner | RiskProximity | Probability | Severity | RiskRating | Prob | MinImpact | MostLikelyImpact | MaxImpact | CurrentRiskValue | Justification | Manageability | Probability2 | Severity3 | Risk Rating | OverallStatus | Date Closed | Date Reviewed | Date Added
M.Faraday | pending | GLDS_001 | Opportunity | Project Sunset | 04- Design | Project Acceleration Opportunity | There is an opportunity that the programme can be accelerated on Project Sunset | Caused by improved performance of design team | Resulting in potential programme acceleration and ability to start construction earlier | A.Turing | 0-3 months | 3 | -5 | -15 | 50% | 0 | 0 | -25000000 | -4166666.6667 | Min - ML - Max- Cost per week of 8 weeks saving | Reasonable Ability to Influence & Manage | 4 | -5 | -20 | CLOSED - CE | 2022-11-08 | 2022-08-24 | 2022-08-24
R.Franklin | approved | GLDS_002 | Threat | Project Dejavu | 06- Construction | Supply Chain Buy-In | There is a risk that the supply chain are do not buy into construction programme | Caused by the supply chain having limited input to the latest schedule | Resulting in potential changes to the construction programme and subsequent knock-on effects | M.Faraday | Now | 3 | 5 | 15 | 50% | 0 | 5000000 | 15000000 | 3333333.3333 | Min- No impact and deliver ML- 4 week impact (renegotiating/resource allocation delays) Max- 12 week impact associated with having to retender packages where contractors cannot meet the programme. Knock-on to other trades | Strong Ability to Influence & Manage | 3 | 3 | 9 | CLOSED - CE | 2022-12-01 | 2022-10-31 | 2022-08-11
L.Da Vinci | rejected | GLDS_003 | Threat | Project Dejavu | 08- Operations / Maintenance | Commissioning Programme Lacks Robustness | There is a risk that the commissioning programme is not robust enough i.e. no terminal float | Caused by limited programme float and a process still to be agreed | Resulting in commissioning programme delay or overrun subsequently delaying Project Dejavu opening | M.Faraday | 6-12 months | 2 | 5 | 10 | 25% | 0 | 1000000 | 5000000 | 500000 | Min- No impact and deliver ML- 2 week impact Max- 8 week impact associated Operations delay in handover approval | Low Ability to Influence & Manage | 1 | 4 | 4 | CLOSED - EWN | 2022-11-15 | 2022-09-22 | 2022-07-21
I.Newton | pending | GLDS_004 | Threat | Corporate | 09- Corporate | Unable to resource specialists | There is a risk that the projects are unable to secure specialist resources to enable delivery of their programme | Caused by limited specialist resource in the marketplace and HR delays | Resulting in delays to programme caused by under resourcing | M.Curie | 0-3 months | 5 | 2 | 10 | 75% | 0 | 50000 | 75000 | 31250 | Min- No impact ML- Min delay, but premium paid in some instances Max- Associated delay with being unable to secure specialist resource up to 6 weeks (linked to any overall programme) | Strong Ability to Influence & Manage | 3 | 3 | 9 | CLOSED | 2023-01-21 | 2022-10-13 | 2022-10-08
L.Da Vinci | pending | GLDS_005 | Threat | Project Sunset | 06- Construction | Knowledge gaps | There is a risk that the existing project team disappear as the project heads to conclusion leaving critical knowledge gaps | Caused by a buoyant construction market and inability to secure key resource to project end | Resulting in loss of critical project knowledge, potentially delaying contentious sign-off areas | A.Turing | 6-12 months | 3 | 2 | 6 | 40% | 100000 | 250000 | 500000 | 113333.3333 | Min- 3 Key People ML - 7 Key People Max- Assumed 10 Key People @ £50k | Reasonable Ability to Influence & Manage | 3 | 2 | 6 | CLOSED | 2022-12-29 | 2022-11-05 | 2022-10-28
R.Franklin | pending | GLDS_006 | Threat | Project Dejavu | 04- Design | Late Design Issues | There is a risk that there are more design issues at large that have yet to be uncovered | Caused by not all design being frozen and procurement activities outstanding | Resulting in delay to procurement and construction programme | J.Maxwell | 0-3 months | 3 | 4 | 12 | 50% | 1000000 | 5000000 | 15000000 | 3500000 | Min- Minimal impact ML- Additional resource costing and a level of delay (disruption and additional work) Max- Additional delays and design resource costings with knock-on impacts on rework | Low Ability to Influence & Manage | 2 | 4 | 8 | CLOSED - EWN | 2023-05-15 | 2022-11-11 | 2022-09-06
N.Tesla | approved | GLDS_007 | Threat | Project Whistler | 07- Technical | Quantum of Rework | There is a risk that the quantum of rework does not reduce | Caused by significant volume of existing rework and potential future rework | Resulting in inability to perform to programme and increased aftercare/defect costs | N.Tesla | Now | 3 | 5 | 15 | 50% | 1000000 | 5000000 | 7500000 | 2250000 | Min- Minimal impact ML- Additional resource costing and a level of delay (disruption and additional work) Max- Additional delays and design resource costings with knock-on impacts on rework | Low Ability to Influence & Manage | 2 | 5 | 10 | OPEN | 2023-06-28 | 2022-10-13 | 2022-09-08
A.Turing | approved | GLDS_008 | Threat | Project Whistler | 07- Technical | Commissioning Failure | There is a risk of system integration failure/faults etc that arise in Commissioning causing significant rework | Caused by complexity associated with commissioning and compliance | Resulting in significant rework | N.Tesla | Now | 3 | 2 | 6 | 40% | 50000 | 200000 | 750000 | 133333.3333 | Min- ML- Increased costs associated with rework but min prog delay Max- Critical delay with additional equipment required and rework | Reasonable Ability to Influence & Manage | 2 | 2 | 4 | OPEN | 2023-04-01 | 2022-11-05 | 2022-07-26
L.Pasteur | approved | GLDS_009 | Threat | Project Dejavu | 05- Commercial/ Procurement | Handover Documentation | There is a risk that the level of handover documentation is underestimated causing programme delay | Caused by underestimation of handover documentation required and approval process | Resulting in handover programme delay | J.Maxwell | 6-9 months | 3 | 2 | 6 | 40% |  | 300000 | 6000000 | 1260000 | Best case is no impact - zero Worst case would be a 4 week delay - currently project monthly spend as £ 1.5m | Strong Ability to Influence & Manage | 2 | 2 | 4 | CLOSED | 2022-12-13 | 2022-11-29 | 2022-11-26
N.Tesla | approved | GLDS_010 | Threat | Corporate | 09- Corporate | Fire & Safety Bill underestimation | There is a risk that the imminent updates to the Fire & Safety Bill are underestimated/implemented too late | Caused by lack of understanding of the latest Fire & Safety Bill changes | Resulting in increased requirements for records and records keeping that put additional strain on project programme and resources | R.Franklin | Now | 3 | 4 | 12 | 40% | 0 | 3000000 | 4000000 | 933333.3333 | Best case is no impact - zero Worst case open up facades and reinstall all fire safety. 4 weeks impact @ £1m per week | Low Ability to Influence & Manage | 1 | 5 | 5 | OPEN | 2023-01-26 | 2022-08-18 | 2022-07-23
N.Tesla | approved | GLDS_011 | Threat | Corporate | 09- Corporate | New Legislation | There is a risk that new legislation/ways working require to be applied retrospectively | Caused by changes in legislation and ways of working since the project began | Resulting in late changes to design, construction and commissioning | R.Franklin | 12-15 months | 1 | 5 | 5 | 5% | 0 | 0 | 10000000 | 166666.6667 | Max- Impact presumed to apply to all projects | Low Ability to Influence & Manage | 1 | 3 | 3 | CLOSED - EWN | 2022-11-29 | 2022-11-01 | 2022-10-17
N.Tesla | approved | GLDS_012 | Threat | Project Sunset | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | A.Turing | Now | 4 | 4 | 8 | 60% | 50000 | 100000 | 800000 | 190000 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust require re-procured | Reasonable Ability to Influence & Manage | 4 | 2 | 8 | CLOSED - EWN | 2023-03-23 | 2022-11-18 | 2022-11-14
A.Turing | approved | GLDS_013 | Threat | Project Dejavu | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | I.Newton | 6-9 months | 2 | 2 | 8 | 20% | 0 | 100000 | 400000 | 33333.3333 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust requiring replacing and associated delays (Reprocure and Premium costs) | Reasonable Ability to Influence & Manage | 1 | 2 | 2 | CLOSED - CE | 2023-03-01 | 2022-11-24 | 2022-09-12
M.Faraday | approved | GLDS_014 | Threat | Project Whistler | 05- Commercial/ Procurement | Contractor insolvency | There is a risk that some trade contractors could go bust if they face insolvency challenges | Caused by ongoing market pressures/challenges | Resulting in abortive work and potential contractor replacement | I.Newton | 6-9 months | 4 | 2 | 8 | 55% | 0 | 100000 | 400000 | 91666.6667 | Min- No impact ML- Challenges faced by some contractors (non-critical/easily replaced) so minimal impact Max- Key critical path trades go bust requiring replacing and associated delays (Reprocure and Premium costs) | Reasonable Ability to Influence & Manage | 2 | 2 | 4 | OPEN | 2022-12-16 | 2022-09-23 | 2022-09-19
M.Faraday | approved | GLDS_015 | Threat | Corporate | 05- Commercial/ Procurement | Increased Inflation | There is a risk of increased inflation to materials and labour that impacts all projects | Caused by project allowances not being sufficient to meet future inflation changes | Resulting in increased Corporate Funding costs for all projects | I.Newton | Now | 3 | 5 | 15 | 66% | 0 | 5000000 | 25000000 | 6600000 | ML- £1m per project Max- £5m per project | Low Ability to Influence & Manage | 2 | 2 | 4 | CLOSED - CE | 2023-04-11 | 2022-09-11 | 2022-08-31
J.Maxwell | pending | GLDS_016 | Threat | Project Whistler | 07- Technical | Equipment availability | There is a risk that due to the previous prog delay that some equipment is no longer available | Caused by required equipment now being obsolete | Resulting in further delay associated with re-procurement and design changes in relation to spacing/room conditions | N.Tesla | 6-9 months | 1 | 4 | 4 | 35% | 600000 | 1500000 | 4000000 | 711666.6667 | Max- impact on all systems - 4 months total impact and systems reconfigured | Strong Ability to Influence & Manage | 1 | 4 | 4 | OPEN | 2022-09-10 | 2022-08-20 | 2022-07-06
R.Franklin | pending | GLDS_017 | Threat | Project Whistler | 08- Operations / Maintenance | Lack of extended warranties | There is a risk that due to the prog delay that equipment already purchased will require extended warranties or extended warranties will not be possible | Caused by overall programme delay and some equipment already being in receipt | Resulting in additional project costs to extend warranties | N.Tesla | 6-9 months | 3 | 1 | 3 | 30% | 10000 | 20000 | 50000 | 8000 | Max- Extended Warranties of 5 systems required | Strong Ability to Influence & Manage | 1 | 2 | 2 | CLOSED | 2023-03-30 | 2022-10-20 | 2022-10-09
M.Faraday | Rejected | GLDS_018 | Threat | Project Dejavu | 03- Existing Assets | Utilities Failure | There is a risk that any Utilities (Water, Power, Gas, Telecom) fail or is insufficient | Caused by performance issues associated with given utility | Resulting in additional rework and programme delay | M.Faraday | Now | 2 | 4 | 8 | 20% | 0 | 750000 | 2500000 | 216666.6667 | Max- All Utilities fail | Strong Ability to Influence & Manage | 1 | 1 | 1 | CLOSED - EWN | 2023-06-13 | 2022-11-11 | 2022-10-31
L.Pasteur | approved | GLDS_019 | Threat | Project Whistler | 01- Strategic/ Programme | Culture & Behaviours | There is a risk that given the projects past performance can the project team change behaviours sufficiently to allow collaboration across the project to drive performance. | Caused by historical project behaviours and lack of collaborative ways of working | Resulting in challenging project delivery and potential further delays | M.Curie | 0-3 months | 5 | 5 | 25 | 50% | 0 | 100000 | 3000000 | 516666.6667 |  | Low Ability to Influence & Manage | 3 | 3 | 9 | OPEN | 2022-12-31 | 2022-11-10 | 2022-07-05
M.Curie | approved | GLDS_020 | Threat | Project Sunset | 01- Strategic/ Programme | Culture & Behaviours | There is a risk that given the projects past performance can the project team change behaviours sufficiently to allow collaboration across the project to drive performance. | Caused by historical project behaviours and lack of collaborative ways of working | Resulting in challenging project delivery and potential further delays | M.Curie | 0-3 months | 3 | 5 | 15 | 50% | 0 | 100000 | 500000 | 100000 |  | Low Ability to Influence & Manage | 3 | 3 | 9 | CLOSED - CE | 2022-12-23 | 2022-11-05 | 2022-09-26
N.Tesla | pending | GLDS_021 | Threat | Project Sunset | 03- Existing Assets | Utilities Failure | There is a risk that any Utilities (Water, Power, Gas, Telecom) fail or is insufficient | Caused by performance issues associated with given utility | Resulting in additional rework and programme delay | A.Turing | Now | 5 | 4 | 20 | 80% | 0 | 7500000 | 10000000 | 4666666.6667 | Max- All Utilities fail re. full redesign and remediation | Low Ability to Influence & Manage | 3 | 5 | 15 | CLOSED - EWN | 2023-02-14 | 2022-10-21 | 2022-09-30
L.Da Vinci | pending | GLDS_022 | Opportunity | Project Sunset | 05- Commercial/ Procurement | Opportunity to In-House Procure | There is an opportunity for the in-house delivery team to conduct the works rather than externals | Caused by recent recruitment of technical specialists | Resulting in 'costs' to deliver being diverted internally | A.Turing | Now | 4 | -2 | -8 | 95% | -25000 | -200000 | -1000000 | -387916.6667 | Max- All delivery contracts diverted internally | Strong Ability to Influence & Manage | 5 | -2 | -10 | CLOSED - EWN | 2023-01-11 | 2022-11-24 | 2022-09-11
M.Curie | pending | GLDS_023 | Threat | Corporate | 09- Corporate | Lack of funding for Christmas Parties | There is a risk that due to poor corporate performance there is no budget for Christmas parties | Caused by poor investment decisions and delay in procuring Project Whistler | Resulting in poor staff morale and reputational damage | R.Franklin | Now | 5 | 2 | 10 | 90% | 0 | 100000 | 275000 | 112500 | Max- Staff replacement/recruitment costs | Reasonable Ability to Influence & Manage | 4 | 1 | 4 | CLOSED | 2023-03-07 | 2022-11-28 | 2022-11-17
M.Faraday | pending | GLDS_024 | Threat | Corporate | 01- Strategic/ Programme | Project Whistler Mothball | There is a risk that the SLT decide to mothball Project Whistler | Caused by poor project and team performance and potential lack of RoI | Resulting in significant revenue stream loss and reputational damage | R.Franklin | 3-6 months | 4 | 5 | 20 | 75% | 5000000 | 12500000 | 20000000 | 9375000 | ML- Revenue loss Max- Investor repayment and revenue loss | Low Ability to Influence & Manage | 3 | 4 | 12 | CLOSED | 2023-04-14 | 2022-09-27 | 2022-07-01
M.Faraday | rejected | GLDS_025 | Threat | Project Sunset | 01- Strategic/ Programme | RiskTitle GLDS_025 | RiskDescription GLDS_025 | RiskCause GLDS_025 | RiskConsequence GLDS_025 | L.Da Vinci | Now | 1 | 5 | 5 | 5% | 3000000 | 5179787 | 10000000 | 302996.45 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 0 | 4 | 0 | OPEN | 2023-04-10 | 2022-09-06 | 2022-08-25
R.Franklin | approved | GLDS_026 | Opportunity | Project Whistler | 07- Technical | RiskTitle GLDS_026 | RiskDescription GLDS_026 | RiskCause GLDS_026 | RiskConsequence GLDS_026 | M.Curie | 3-6 months | 1 | 5 | 5 | 5% | 3000000 | 7704752 | 10000000 | 345079.2 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 2 | 6 | -12 | CLOSED - CE | 2023-05-27 | 2022-10-25 | 2022-10-15
L.Da Vinci | approved | GLDS_027 | Threat | Corporate | 03- Existing Assets | RiskTitle GLDS_027 | RiskDescription GLDS_027 | RiskCause GLDS_027 | RiskConsequence GLDS_027 | L.Pasteur | 9-12 months | 5 | 4 | 20 | 85% | 1000000 | 2971206 | 2999999 | 1975174.75 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 4 | 3 | 12 | CLOSED - EWN | 2022-11-15 | 2022-09-22 | 2022-07-21
I.Newton | rejected | GLDS_028 | Opportunity | Project Dejavu | 03- Existing Assets | RiskTitle GLDS_028 | RiskDescription GLDS_028 | RiskCause GLDS_028 | RiskConsequence GLDS_028 | L.Pasteur | Now | 5 | 4 | 20 | 85% | 1000000 | 2479508 | 2999999 | 1835860.3167 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Reasonable Ability to Influence & Manage | 6 | 5 | -30 | CLOSED | 2023-01-21 | 2022-10-13 | 2022-10-08
L.Da Vinci | approved | GLDS_029 | Opportunity | Corporate | 03- Existing Assets | RiskTitle GLDS_029 | RiskDescription GLDS_029 | RiskCause GLDS_029 | RiskConsequence GLDS_029 | L.Da Vinci | 12+ months | 4 | 3 | 12 | 65% | 500000 | 802210 | 999000 | 498595.5 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 5 | 4 | -20 | CLOSED | 2022-12-29 | 2022-11-05 | 2022-10-28
R.Franklin | approved | GLDS_030 | Threat | Corporate | 05- Commercial/ Procurement | RiskTitle GLDS_030 | RiskDescription GLDS_030 | RiskCause GLDS_030 | RiskConsequence GLDS_030 | A.Turing | 9-12 months | 1 | 2 | 2 | 5% | 50000 | 312273 | 499000 | 14354.55 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 0 | 1 | 0 | CLOSED - EWN | 2023-05-15 | 2022-11-11 | 2022-09-06
N.Tesla | approved | GLDS_031 | Opportunity | Project Sunset | 05- Commercial/ Procurement | RiskTitle GLDS_031 | RiskDescription GLDS_031 | RiskCause GLDS_031 | RiskConsequence GLDS_031 | I.Newton | 0-3 months | 1 | 4 | 4 | 5% | 1000000 | 1403451 | 2999999 | 90057.5 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Reasonable Ability to Influence & Manage | 2 | 5 | -10 | OPEN | 2023-06-28 | 2022-10-13 | 2022-09-08
A.Turing | rejected | GLDS_032 | Opportunity | Corporate | 05- Commercial/ Procurement | RiskTitle GLDS_032 | RiskDescription GLDS_032 | RiskCause GLDS_032 | RiskConsequence GLDS_032 | N.Tesla | 0-3 months | 2 | 5 | 10 | 20% | 3000000 | 3323537 | 10000000 | 1088235.8 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 3 | 6 | -18 | OPEN | 2023-04-01 | 2022-11-05 | 2022-07-26
L.Pasteur | approved | GLDS_033 | Threat | Project Whistler | 04- Design | RiskTitle GLDS_033 | RiskDescription GLDS_033 | RiskCause GLDS_033 | RiskConsequence GLDS_033 | I.Newton | 9-12 months | 3 | 1 | 3 | 40% | 0 | 34025 | 49000 | 11070 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 2 | 0 | 0 | CLOSED | 2022-12-13 | 2022-11-29 | 2022-11-26
N.Tesla | approved | GLDS_034 | Opportunity | Corporate | 01- Strategic/ Programme | RiskTitle GLDS_034 | RiskDescription GLDS_034 | RiskCause GLDS_034 | RiskConsequence GLDS_034 | M.Faraday | 0-3 months | 4 | 1 | 4 | 65% | 0 | 5888 | 49000 | 11892.4 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 5 | 2 | -10 | OPEN | 2023-01-26 | 2022-08-18 | 2022-07-23
N.Tesla | approved | GLDS_035 | Opportunity | Corporate | 05- Commercial/ Procurement | RiskTitle GLDS_035 | RiskDescription GLDS_035 | RiskCause GLDS_035 | RiskConsequence GLDS_035 | M.Curie | 6-9 months | 5 | 3 | 15 | 85% | 500000 | 756300 | 999000 | 639001.6667 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 6 | 4 | -24 | CLOSED - EWN | 2022-11-29 | 2022-11-01 | 2022-10-17
N.Tesla | approved | GLDS_036 | Opportunity | Project Dejavu | 05- Commercial/ Procurement | RiskTitle GLDS_036 | RiskDescription GLDS_036 | RiskCause GLDS_036 | RiskConsequence GLDS_036 | M.Curie | 6-9 months | 2 | 4 | 8 | 20% | 1000000 | 2447509 | 2999999 | 429833.8667 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 3 | 5 | -15 | CLOSED - EWN | 2023-03-23 | 2022-11-18 | 2022-11-14
A.Turing | pending | GLDS_037 | Threat | Project Whistler | 03- Existing Assets | RiskTitle GLDS_037 | RiskDescription GLDS_037 | RiskCause GLDS_037 | RiskConsequence GLDS_037 | M.Curie | 9-12 months | 1 | 3 | 3 | 5% | 500000 | 667202 | 999000 | 36103.3667 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Reasonable Ability to Influence & Manage | 0 | 2 | 0 | CLOSED - CE | 2023-03-01 | 2022-11-24 | 2022-09-12
M.Faraday | pending | GLDS_038 | Threat | Project Whistler | 08- Operations / Maintenance | RiskTitle GLDS_038 | RiskDescription GLDS_038 | RiskCause GLDS_038 | RiskConsequence GLDS_038 | L.Pasteur | 3-6 months | 1 | 2 | 2 | 5% | 50000 | 205493 | 499000 | 12574.8833 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 0 | 1 | 0 | OPEN | 2022-12-16 | 2022-09-23 | 2022-09-19
M.Faraday | pending | GLDS_039 | Threat | Corporate | 02- Planning | RiskTitle GLDS_039 | RiskDescription GLDS_039 | RiskCause GLDS_039 | RiskConsequence GLDS_039 | J.Maxwell | 6-9 months | 2 | 5 | 10 | 20% | 3000000 | 7587890 | 10000000 | 1372526 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 1 | 4 | 4 | CLOSED - CE | 2023-04-11 | 2022-09-11 | 2022-08-31
J.Maxwell | rejected | GLDS_040 | Threat | Project Whistler | 02- Planning | RiskTitle GLDS_040 | RiskDescription GLDS_040 | RiskCause GLDS_040 | RiskConsequence GLDS_040 | N.Tesla | 12+ months | 4 | 1 | 4 | 65% | 0 | 20033 | 49000 | 14957.15 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 3 | 0 | 0 | OPEN | 2022-09-10 | 2022-08-20 | 2022-07-06
R.Franklin | pending | GLDS_041 | Opportunity | Corporate | 08- Operations / Maintenance | RiskTitle GLDS_041 | RiskDescription GLDS_041 | RiskCause GLDS_041 | RiskConsequence GLDS_041 | L.Da Vinci | 3-6 months | 2 | 3 | 6 | 20% | 500000 | 755888 | 999000 | 150325.8667 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 3 | 4 | -12 | CLOSED | 2023-03-30 | 2022-10-20 | 2022-10-09
M.Faraday | approved | GLDS_042 | Threat | Project Dejavu | 02- Planning | RiskTitle GLDS_042 | RiskDescription GLDS_042 | RiskCause GLDS_042 | RiskConsequence GLDS_042 | A.Turing | 3-6 months | 5 | 5 | 25 | 85% | 3000000 | 5282513 | 10000000 | 5180045.35 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 4 | 4 | 16 | CLOSED - EWN | 2023-06-13 | 2022-11-11 | 2022-10-31
L.Pasteur | approved | GLDS_043 | Threat | Project Sunset | 01- Strategic/ Programme | RiskTitle GLDS_043 | RiskDescription GLDS_043 | RiskCause GLDS_043 | RiskConsequence GLDS_043 | J.Maxwell | 6-9 months | 2 | 3 | 6 | 20% | 500000 | 768184 | 999000 | 151145.6 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Reasonable Ability to Influence & Manage | 1 | 2 | 2 | OPEN | 2022-12-31 | 2022-11-10 | 2022-07-05
M.Curie | approved | GLDS_044 | Threat | Corporate | 04- Design | RiskTitle GLDS_044 | RiskDescription GLDS_044 | RiskCause GLDS_044 | RiskConsequence GLDS_044 | J.Maxwell | 6-9 months | 4 | 3 | 12 | 65% | 500000 | 843489 | 999000 | 507539.2833 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 3 | 2 | 6 | CLOSED - CE | 2022-12-23 | 2022-11-05 | 2022-09-26
N.Tesla | pending | GLDS_045 | Threat | Corporate | 03- Existing Assets | RiskTitle GLDS_045 | RiskDescription GLDS_045 | RiskCause GLDS_045 | RiskConsequence GLDS_045 | R.Franklin | Now | 5 | 1 | 5 | 85% | 0 | 13273 | 49000 | 17644.0167 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Low Ability to Influence & Manage | 4 | 0 | 0 | CLOSED - EWN | 2023-02-14 | 2022-10-21 | 2022-09-30
L.Da Vinci | approved | GLDS_046 | Opportunity | Project Sunset | 06- Construction | RiskTitle GLDS_046 | RiskDescription GLDS_046 | RiskCause GLDS_046 | RiskConsequence GLDS_046 | M.Faraday | Now | 2 | 5 | 10 | 20% | 3000000 | 9263087 | 10000000 | 1484205.8 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 3 | 6 | -18 | CLOSED - EWN | 2023-01-11 | 2022-11-24 | 2022-09-11
M.Curie | approved | GLDS_047 | Threat | Project Sunset | 06- Construction | RiskTitle GLDS_047 | RiskDescription GLDS_047 | RiskCause GLDS_047 | RiskConsequence GLDS_047 | J.Maxwell | 9-12 months | 2 | 4 | 8 | 20% | 1000000 | 2122851 | 2999999 | 408190 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Reasonable Ability to Influence & Manage | 1 | 3 | 3 | CLOSED | 2023-03-07 | 2022-11-28 | 2022-11-17
M.Faraday | approved | GLDS_048 | Opportunity | Project Sunset | 08- Operations / Maintenance | RiskTitle GLDS_048 | RiskDescription GLDS_048 | RiskCause GLDS_048 | RiskConsequence GLDS_048 | M.Curie | Now | 5 | 3 | 15 | 85% | 500000 | 689714 | 999000 | 620135.6333 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 6 | 4 | -24 | CLOSED | 2023-04-14 | 2022-09-27 | 2022-07-01
N.Tesla | approved | GLDS_049 | Opportunity | Project Dejavu | 03- Existing Assets | RiskTitle GLDS_049 | RiskDescription GLDS_049 | RiskCause GLDS_049 | RiskConsequence GLDS_049 | M.Faraday | 0-3 months | 2 | 4 | 8 | 20% | 1000000 | 2664715 | 2999999 | 444314.2667 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 3 | 5 | -15 | OPEN | 2023-04-10 | 2022-09-06 | 2022-08-25
A.Turing | pending | GLDS_050 | Opportunity | Project Dejavu | 04- Design | RiskTitle GLDS_050 | RiskDescription GLDS_050 | RiskCause GLDS_050 | RiskConsequence GLDS_050 | M.Curie | 3-6 months | 4 | 3 | 12 | 65% | 500000 | 997326 | 999000 | 540870.6333 | Min - Justification for Min ML - Justification for Most Likely Max- Justification for Max | Strong Ability to Influence & Manage | 5 | 4 | -20 | CLOSED - CE | 2023-05-27 | 2022-10-25 | 2022-10-15

## Dropdowns
|  |  | Project List |  | WBS |  | Risk Proximity | 1 | Risk Status |  | Manageability |  | Risk Owner
1 | Threat | 1 | Corporate | 1 | 01- Strategic/ Programme | 1 | Now | 2 | OPEN | 1 | Strong Ability to Influence & Manage | 1 | A.Turing
2 | Opportunity | 2 | Project Dejavu | 2 | 02- Planning | 2 | 0-3 months | 3 | CLOSED | 2 | Reasonable Ability to Influence & Manage | 2 | I.Newton
|  | 3 | Project Sunset | 3 | 03- Existing Assets | 3 | 3-6 months | 4 | CLOSED - EWN | 3 | Low Ability to Influence & Manage | 3 | J.Maxwell
|  | 4 | Project Whistler | 4 | 04- Design | 4 | 6-9 months | 5 | CLOSED - CE |  |  | 4 | L.Da Vinci
|  |  |  | 5 | 05- Commercial/ Procurement | 5 | 9-12 months |  |  |  |  | 5 | L.Pasteur
|  |  |  | 6 | 06- Construction | 6 | 12+ months |  |  |  |  | 6 | M.Curie
|  |  |  | 7 | 07- Technical | [6 empty] | 7 | M.Faraday
|  |  |  | 8 | 08- Operations / Maintenance | [6 empty] | 8 | N.Tesla
|  |  |  | 9 | 09- Corporate | [6 empty] | 9 | R.Franklin
|  | 1 | pending
|  | 2 | approved
|  | 3 | rejected
|  | 4 | approved
|  | 5 | approved
|  | 6 | pending

## Hack Action Register
RiskID | DateAdded | ActionID | ActionDetail | ActionOwner | DateDue | UpdateNotes | ActionStatus
GLDS_023 | 2022-11-21 | 1 | Action Detail | L.Da Vinci | 2022-11-21 |  | CLOSED
GLDS_046 | 2022-09-02 | 2 | Action Detail | R.Franklin | 2022-11-26 |  | CLOSED
GLDS_054 | 2022-07-24 | 3 | Action Detail | L.Pasteur | 2022-12-21 |  | CLOSED
GLDS_003 | 2022-09-01 | 4 | Action Detail | L.Pasteur | 2022-12-30 |  | OPEN
GLDS_036 | 2022-09-08 | 5 | Action Detail | I.Newton | 2022-09-27 |  | CLOSED
GLDS_011 | 2022-08-24 | 6 | Action Detail | L.Pasteur | 2023-02-18 |  | OPEN
GLDS_029 | 2022-09-21 | 7 | Action Detail | J.Maxwell | 2022-12-26 |  | CLOSED
GLDS_012 | 2022-10-07 | 8 | Action Detail | M.Curie | 2023-01-23 |  | CLOSED
GLDS_009 | 2022-09-22 | 9 | Action Detail | I.Newton | 2023-02-09 |  | CLOSED
GLDS_048 | 2022-08-15 | 10 | Action Detail | I.Newton | 2022-09-26 |  | CLOSED
GLDS_033 | 2022-11-20 | 11 | Action Detail | M.Faraday | 2023-01-15 |  | CLOSED
GLDS_030 | 2022-07-23 | 12 | Action Detail | M.Faraday | 2022-12-31 |  | OPEN
GLDS_043 | 2022-10-20 | 13 | Action Detail | M.Curie | 2022-12-05 |  | OPEN
GLDS_006 | 2022-11-23 | 14 | Action Detail | L.Pasteur | 2022-12-02 |  | CLOSED
GLDS_018 | 2022-10-20 | 15 | Action Detail | R.Franklin | 2022-11-23 |  | CLOSED
GLDS_016 | 2022-11-08 | 16 | Action Detail | L.Da Vinci | 2023-01-06 |  | OPEN
GLDS_025 | 2022-09-23 | 17 | Action Detail | L.Pasteur | 2023-02-14 |  | CLOSED
GLDS_014 | 2022-10-05 | 18 | Action Detail | A.Turing | 2022-11-03 |  | CLOSED
GLDS_001 | 2022-09-16 | 19 | Action Detail | M.Curie | 2023-02-16 |  | CLOSED
GLDS_024 | 2022-10-25 | 20 | Action Detail | L.Pasteur | 2023-02-27 |  | OPEN
GLDS_008 | 2022-10-14 | 21 | Action Detail | R.Franklin | 2022-12-13 |  | OPEN
GLDS_007 | 2022-07-30 | 22 | Action Detail | M.Curie | 2022-09-23 |  | CLOSED
GLDS_049 | 2022-09-17 | 23 | Action Detail | M.Curie | 2022-11-28 |  | CLOSED
GLDS_039 | 2022-08-07 | 24 | Action Detail | L.Pasteur | 2022-11-07 |  | CLOSED
GLDS_026 | 2022-08-05 | 25 | Action Detail | R.Franklin | 2023-01-21 |  | OPEN
GLDS_002 | 2022-07-13 | 26 | Action Detail | J.Maxwell | 2022-10-14 |  | CLOSED
GLDS_050 | 2022-10-10 | 27 | Action Detail | N.Tesla | 2022-12-01 |  | OPEN
GLDS_018 | 2022-11-04 | 28 | Action Detail | J.Maxwell | 2023-01-16 |  | OPEN
GLDS_033 | 2022-11-20 | 29 | Action Detail | A.Turing | 2023-01-17 |  | OPEN
GLDS_001 | 2022-11-18 | 30 | Action Detail | N.Tesla | 2023-02-12 |  | OPEN
GLDS_052 | 2022-08-21 | 31 | Action Detail | A.Turing | 2023-01-15 |  | CLOSED
GLDS_033 | 2022-08-08 | 32 | Action Detail | L.Da Vinci | 20/012/2022 |  | OPEN
GLDS_052 | 2022-11-07 | 33 | Action Detail | L.Pasteur | 2023-01-02 |  | OPEN
GLDS_040 | 2022-08-30 | 34 | Action Detail | M.Faraday | 2022-10-15 |  | CLOSED
GLDS_053 | 2022-11-10 | 35 | Action Detail | R.Franklin | 2023-02-02 |  | CLOSED
GLDS_045 | 2022-10-01 | 36 | Action Detail | R.Franklin | 2022-11-27 |  | CLOSED
GLDS_044 | 2022-08-24 | 37 | Action Detail | L.Pasteur | 2022-12-21 |  | OPEN
GLDS_016 | 2022-11-24 | 38 | Action Detail | L.Da Vinci | 2023-02-12 |  | OPEN
GLDS_008 | 2022-10-31 | 39 | Action Detail | N.Tesla | 2023-01-17 |  | CLOSED
GLDS_013 | 2022-10-23 | 40 | Action Detail | L.Da Vinci | 2023-01-01 |  | CLOSED
GLDS_026 | 2022-10-07 | 41 | Action Detail | I.Newton | 2022-11-04 |  | CLOSED
GLDS_028 | 2022-09-25 | 42 | Action Detail | M.Curie | 2023-02-13 |  | OPEN
GLDS_023 | 2022-09-18 | 43 | Action Detail | J.Maxwell | 2023-02-02 |  | CLOSED
GLDS_023 | 2022-11-20 | 44 | Action Detail | R.Franklin | 2023-02-01 |  | CLOSED
GLDS_009 | 2022-11-15 | 45 | Action Detail | N.Tesla | 2022-11-25 |  | CLOSED
GLDS_046 | 2022-09-07 | 46 | Action Detail | A.Turing | 2022-10-21 |  | CLOSED
GLDS_023 | 2022-07-25 | 47 | Action Detail | R.Franklin | 2023-01-01 |  | OPEN
GLDS_047 | 2022-11-02 | 48 | Action Detail | A.Turing | 2022-11-08 |  | CLOSED
GLDS_007 | 2022-10-03 | 49 | Action Detail | R.Franklin | 2022-12-03 |  | CLOSED
GLDS_004 | 2022-07-04 | 50 | Action Detail | R.Franklin | 2022-07-30 |  | CLOSED
GLDS_006 | 2022-08-30 | 51 | Action Detail | A.Turing | 2022-10-04 |  | CLOSED
GLDS_039 | 2022-08-13 | 52 | Action Detail | M.Curie | 2022-09-03 |  | CLOSED
GLDS_013 | 2022-09-26 | 53 | Action Detail | M.Curie | 2022-10-28 |  | CLOSED
GLDS_002 | 2022-07-19 | 54 | Action Detail | I.Newton | 2022-08-11 |  | CLOSED
GLDS_029 | 2022-08-25 | 55 | Action Detail | L.Pasteur | 2022-10-23 |  | CLOSED
GLDS_002 | 2022-10-19 | 56 | Action Detail | L.Pasteur | 2022-11-22 |  | CLOSED
GLDS_010 | 2022-08-26 | 57 | Action Detail | L.Da Vinci | 2022-11-04 |  | CLOSED
GLDS_032 | 2022-08-16 | 58 | Action Detail | N.Tesla | 2022-12-19 |  | OPEN
GLDS_010 | 2022-08-08 | 59 | Action Detail | L.Da Vinci | 2023-01-22 |  | CLOSED
GLDS_030 | 2022-10-15 | 60 | Action Detail | J.Maxwell | 2023-03-01 |  | OPEN
GLDS_040 | 2022-10-22 | 61 | Action Detail | R.Franklin | 2022-12-25 |  | OPEN
GLDS_053 | 2022-09-06 | 62 | Action Detail | I.Newton | 2022-11-19 |  | CLOSED
GLDS_007 | 2022-10-30 | 63 | Action Detail | L.Pasteur | 2023-02-02 |  | OPEN
GLDS_024 | 2022-07-23 | 64 | Action Detail | L.Da Vinci | 2022-08-12 |  | CLOSED
GLDS_012 | 2022-11-03 | 65 | Action Detail | R.Franklin | 2022-11-03 |  | CLOSED
GLDS_026 | 2022-07-27 | 66 | Action Detail | L.Da Vinci | 2022-08-19 |  | CLOSED
GLDS_053 | 2022-08-12 | 67 | Action Detail | J.Maxwell | 2022-12-13 |  | OPEN
GLDS_043 | 2022-09-24 | 68 | Action Detail | L.Da Vinci | 2023-02-04 |  | OPEN
GLDS_007 | 2022-09-26 | 69 | Action Detail | R.Franklin | 2022-12-18 |  | CLOSED
GLDS_002 | 2022-07-13 | 70 | Action Detail | M.Faraday | 2022-12-30 |  | CLOSED
GLDS_007 | 2022-10-27 | 71 | Action Detail | I.Newton | 2022-11-04 |  | CLOSED
GLDS_001 | 2022-11-04 | 72 | Action Detail | L.Da Vinci | 2023-02-13 |  | OPEN
GLDS_013 | 2022-08-11 | 73 | Action Detail | M.Faraday | 2022-08-14 |  | CLOSED
GLDS_027 | 2022-08-11 | 74 | Action Detail | R.Franklin | 2022-09-09 |  | CLOSED
GLDS_041 | 2022-09-04 | 75 | Action Detail | I.Newton | 2022-11-05 |  | OPEN
GLDS_003 | 2022-10-12 | 76 | Action Detail | L.Da Vinci | 2022-12-21 |  | CLOSED
GLDS_018 | 2022-08-06 | 77 | Action Detail | L.Da Vinci | 2023-01-17 |  | OPEN
GLDS_030 | 2022-08-20 | 78 | Action Detail | N.Tesla | 2022-10-09 |  | OPEN
GLDS_047 | 2022-08-31 | 79 | Action Detail | M.Faraday | 2023-02-28 |  | CLOSED
GLDS_039 | 2022-07-29 | 80 | Action Detail | J.Maxwell | 2022-12-12 |  | OPEN
GLDS_044 | 2022-07-21 | 81 | Action Detail | L.Pasteur | 2022-07-28 |  | CLOSED
GLDS_053 | 2022-10-23 | 82 | Action Detail | M.Faraday | 2023-02-04 |  | CLOSED
GLDS_053 | 2022-11-25 | 83 | Action Detail | A.Turing | 2023-03-01 |  | OPEN
GLDS_042 | 2022-11-08 | 84 | Action Detail | L.Pasteur | 2023-01-30 |  | CLOSED
GLDS_039 | 2022-08-22 | 85 | Action Detail | I.Newton | 2022-11-28 |  | OPEN
GLDS_004 | 2022-11-01 | 86 | Action Detail | M.Faraday | 2022-12-17 |  | OPEN
GLDS_013 | 2022-08-15 | 87 | Action Detail | N.Tesla | 2022-11-17 |  | CLOSED
GLDS_029 | 2022-08-10 | 88 | Action Detail | M.Curie | 2022-11-25 |  | OPEN
GLDS_034 | 2022-11-02 | 89 | Action Detail | L.Pasteur | 2023-01-16 |  | CLOSED
GLDS_021 | 2022-07-01 | 90 | Action Detail | L.Pasteur | 2022-07-05 |  | CLOSED
GLDS_041 | 2022-08-17 | 91 | Action Detail | L.Pasteur | 2023-01-27 |  | OPEN
GLDS_026 | 2022-07-23 | 92 | Action Detail | R.Franklin | 2022-12-16 |  | CLOSED

## Risk Scoring Matrix
Probability |  | Score | Impact
Qualitative | Percentage |  | Capex Cost | Schedule | Qualitative | Key | Status
Very Unlikely | <10% | 1 | <£50k impact | Up to a month delay to non-critical path activities | Very Low | Open | Open
Unlikely | 10-30% | 2 | £50k-£500k | >1 months delay to non-critical path activities | Low | Closed | Closed
Probable | 30-50% | 3 | £500k - £1m | Up to a month delay to critical path activities | Medium | Closed - EWN | Closed - EWN
Likely | 50-80% | 4 | £1m- 3m | 1-3 months delay to critical path activities | High | Closed CE | Closed CE
Highly Likely | >80% | 5 | >£3m | >3 months delay to critical path activities | Very High
|  | 1 | Very Unlikely | 5% |  | Risk Proximity
|  | 2 | Unlikely | 20% |  | Now
|  | 3 | Probable | 40% |  | 0-3 months
|  | 4 | Likely | 65% |  | 0-6 months
|  | 5 | Highly Likely | 85% |  | 0-9 months
0-12 months
0-15months
0-18months
|  | 1 | 0 | 49000 | Very Low | 0-24 months
|  | 2 | 50000 | 499000 | Low | 3-6 months
|  | 3 | 500000 | 999000 | Medium | 6-9 months
|  | 4 | 1000000 | 2999999 | High | 6-12 months
|  | 5 | 3000000 | 10000000 | Very High | 9-12 months
9-15 months
12-15 months