## Sheet1
| Master Risk Register |  |  |  | Actions
| RiskId(GUID) | RiskId |  |  | RiskId | Text(GUID)
|  | AddedBy | Entry Screen | Review Screen | DateAdded | Date
|  | ReviewStatus |  |  | ActionName | Text
Details | Ref | ProjectRef |  | edit | ActionDetail | Text
Details | Threat or Opportunity | ThreatorOpp |  | edit | ActionOwner | Text
Details | Project | Project | edit | edit | UpdateNotes | Text
Details | WBS | WBS | edit | edit | DateDue | Date
Details | Risk Title | RiskTitle | edit | edit | ActionStatus | Text
Details | Risk Description | RiskDescription | edit | edit | Priority | Text
Details | Risk Cause | RiskCause | edit | edit
Details | Risk Consequence | RiskConsequence | edit | edit
Details | Risk Owner | RiskOwner | edit | edit
Details | Risk Proximity | RiskProximity | edit | edit
Current Assessment | Probability (1-5) | Probability |  | edit
Current Assessment | Severity (1-5) | Severity |  | edit
Current Assessment | Risk Rating (1-25) | RiskRating |  | edit
Current Assessment | Prob (%) | Prob |  | edit
Current Assessment | Min Impact (Cost) | MinImpact |  | edit
Current Assessment | Most Likely Impact (Cost) | MostLikelyImpact |  | edit
Current Assessment | Max Impact (Cost) | MaxImpact |  | edit
Current Assessment | Current Risk Value* | CurrentRiskValue |  | edit
Current Assessment | Justification | Justification |  | edit
Mitigation | Manageability | Manageability |  | edit
Mitigation | Probability (1-5) | Probability |  | edit
Mitigation | Severity (1-5) | Severity |  | edit
Mitigation | Risk Rating (1-25) | Risk Rating |  | edit
Mitigation
Mitigation
Mitigation
Updates | Comments/Updates
Updates | Status Open / Closed | OverallStatus |  | edit
Updates | Date Closed | DateClosed |  | edit
Updates | Date Reviewed | DateReviewed |  | edit

## Sheet3
GLDS_001 | Opportunity | Project Sunset | 04- Design | Project Acceleration Opportunity | There is an opportunity that the programme can be accelerated on Project Sunset | Caused by improved performance of design team | Resulting in potential programme acceleration and ability to start construction earlier | A.Turing | 0-3 months | 3 | -5 | -15 | 50% | 0 | 0 | -25000000 | -4166666.6667 | Min - ML - Max- Cost per week of 8 weeks saving | Reasonable Ability to Influence & Manage | Scope lockdown and certainty required. Design team to identify opportunities for time saving and seek approval at earliest moment | 4 | -5 | -20 | A.Turing | 31st Dec 22 | Open | 26.08.22

## Sheet4
A | ProjectRef | GLDS_001 | B | Probability (1-5) | 3
A | ThreatorOpp | Opportunity | B | Severity (1-5) | -5
A | Project | Project Sunset | B | Risk Rating (1-25) | -15
A | WBS | 04- Design | B | Prob (%) | 50%
A | RiskTitle | Project Acceleration Opportunity | B | Min Impact (Cost) | 0
A | RiskDescription | There is an opportunity that the programme can be accelerated on Project Sunset | B | Most Likely Impact (Cost) | 0
A | Risk Cause | Caused by improved performance of design team | B | Max Impact (Cost) | -25000000
A | Risk Consequence | Resulting in potential programme acceleration and ability to start construction earlier | B | Current Risk Value* | -4166666.6667
A | Risk Owner | A.Turing | B | Justification | Min - ML - Max- Cost per week of 8 weeks saving
A | Risk Proximity | 0-3 months
| Manageability | Reasonable Ability to Influence & Manage
| Probability (1-5) | 4
| Severity (1-5) | -5
| Risk Rating (1-25) | -20
| Action Owner (Named Person) | A.Turing
| Action Due Date | 31st Dec 22
| OverallStatus | Open
DateClosed
| DateReviewed | 26.08.22