## query (14)
ActionID | RiskID | DateAdded | ActionDetail | ActionOwner | DateDue | UpdateNotes | ActionStatus | Item Type | Created | Item Type2 | Path
1 | GLDS_001 | 2022-11-27 16:00 | Scope lockdown and certainty required. Design team to identify opportunities for time saving and seek approval at earliest moment | A.Turing | 2022-12-30 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
2 | GLDS_002 | 2022-11-27 16:00 | As early as possible engagement with supply chain required to buy-in to new programme as well as secure available resources | L.Da Vinci | 2022-12-31 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
3 | GLDS_003 | 2022-11-27 16:00 | Sequencing of sectional completion and planned commissioning resource to be test in commission ability reviews Overarching Commissioning Strategy to be completed and approved that outlines responsibilities, deliverables, planned activities etc and is signed up to by all parties | L.Pasteur | 2022-11-30 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
4 | GLDS_004 | 2022-11-27 16:00 | Monitoring of the quantity and type of resource on site compared to the planned level of resources will provide early indications of issues so that action can be taken. | M.Curie | 2023-03-02 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
5 | GLDS_005 | 2022-11-27 16:00 | Ongoing programme to drive Life discussions and capture/disseminate key lessons Consider joint KPIs/ incentives re. retention | M.Curie | 2022-12-30 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
6 | GLDS_006 | 2022-11-27 16:00 | Proactive resolution process in place and needs to be continued i.e. design issues likely to crop up as and when, how the project actively responds is key. | J.Maxwell | 2022-02-28 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
7 | GLDS_007 | 2022-11-27 16:00 | Develop better metrics with BIM 360 and close outs with detailed programmes incorporating the close out sequences and durations. Improve and achieve a consistent level of quality control and avoid repeat issues occurring. | N.Tesla | 2022-10-20 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
8 | GLDS_008 | 2022-11-27 16:00 | Drive programme of improved monitoring and quality controls throughout MEP system integration process. | N.Tesla | 2022-10-20 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
9 | GLDS_009 | 2022-11-27 16:00 | Agree hierarchy and map out responsibilities for documentation handover (i.e. Building and Fire Control) | J.Maxwell | 2023-06-29 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
10 | GLDS_010 | 2022-11-30 09:40 | R.Franklin to ask FS experts to come to all sites and present FS latest | R.Franklin | 2022-12-24 | Following XYZ meeting on XYZ date we have agreed to do this.... | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
11 | GLDS_011 | 2022-11-27 16:00 | Investigate and publish all legislative changes since projects started. Further review to look ahead at current planned legislative changes up to 2024 to enable the direction as required | R.Franklin | 2022-12-25 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
12 | GLDS_012 | 2022-11-27 16:00 | Consider early/advance payment to mitigate insolvency challenges Retain best performing s/c - SME ensure contingency in delivery team | I.Newton | 2022-10-30 | Notes added on dd/mm/yy providing an update to the situation. | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
13 | GLDS_013 | 2022-11-27 16:00 | Consider early/advance payment to mitigate insolvency challenges Retain best performing s/c - SME ensure contingency in delivery team | I.Newton | 2023-02-01 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
14 | GLDS_014 | 2022-11-27 16:00 | Consider early/advance payment to mitigate insolvency challenges Retain best performing s/c - SME ensure contingency in delivery team | I.Newton | 2021-02-28 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
15 | GLDS_015 | 2022-11-27 16:00 | Further review and challenge inflation assumptions/assessments that have been made in the baseline costs. Consider who holds this risk and whether an additional risk allowance is required for /over and above/s/. Could present an opportunity if inflation reduces | I.Newton | 2022-10-30 17:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
16 | GLDS_016 | 2022-11-27 16:00 | Engagement with all equipment suppliers is required when revised dates are know to establish any equipping changes. | N.Tesla | 2022-12-29 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
17 | GLDS_017 | 2022-11-27 16:00 | Clarity required as to which equipment require extended warranties and begin to engage with suppliers This needs to be itemised and quantified to understand the scale of the potential issue. | N.Tesla | 2022-12-30 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
18 | GLDS_018 | 2022-11-27 16:00 | Mitigations completed | M.Faraday | 2022-09-08 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
19 | GLDS_019 | 2022-11-27 16:00 | Collaboration workshops to be set up amongst SLT and project teams Consider project team change as part of sell-off strategy | M.Curie | 2022-11-30 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
20 | GLDS_020 | 2022-11-27 16:00 | Collaboration workshops to be set up amongst SLT and project teams | M.Curie | 2022-12-30 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
21 | GLDS_021 | 2022-11-27 16:00 | 1. Water - Utilities Inc to sign make final connection agreement 2. Gas - GB Gas to confirm incoming supply is sufficient | A.Turing | 2023-01-30 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
22 | GLDS_022 | 2022-11-27 16:00 | Internal team to provide capability statement and proposal for carrying out the works | A.Turing | 2022-12-30 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
23 | GLDS_023 | 2022-11-27 16:00 | Consider deferred Christmas parts to Q1 2023 to allow for potential investments to land | R.Franklin | 2022-12-30 16:00 |  | Open | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
24 | GLDS_024 | 2022-11-27 16:00 | Seek project buy-out investment from Corp X | N.Tesla | 2023-01-30 16:00 |  | Closed | Item | 2022-11-28 14:45 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc
|  |  | Additional action added to manage the issue with another stakeholder. | L.Pasteur | 2022-12-14 |  | Open |  | 2022-11-30 01:23 | Item | sites/Grp_VFDigitalWorkstreams_VFCore/Lists/RiskMastercdc6ffd9750947189d59dc625212b4bc